## Sheet1
Task ID | Task Name | Team | Deadline
PM01 | Discuss with client about look and feel expectation and theme presentation | Product management | 1 day
PM02 | presentation of Sample themes and reference | Product management | 1 day
PM03 | Wireframe with theme presentation and feedback from customer | Product management | 1 day
PM04 | sprint meeting | Product management | 1 day
PM05 | Discuss with client and brainstorm about concept sketch | Product management | 1 day
PM06 | Feedback and changes on Logo first Digital draft | Product management | 1 day
PM07 | Feedback and changes on Logo 2nd Digital draft | Product management | 1 day
7 Days
D01 | Reference and Samples | Design | 1 day
D02 | Website wireframe Design | Design | 3 days
D03 | implementation of theme on wireframe and website mockup Draft 1 for all pages. | Design | 3 days
D04 | Implementing feedback from customer on mockup creating prototype 1 | Design | 1 day
D05 | Logo concept sketch | Design | 1 day
D06 | Logo 1st Digital draft | Design | 1 day
D07 | Logo 2nd Digital draft | Design | 2 days
D08 | Logo final draft | Design | 3 days
D09 | Applying Final changes and handing over logo to development team | Design | 1 day
16 Days
Dev01 | Home/Index page prototype 1 creation | Development | 1 day
Dev02 | Book free consultation form creation for home page | Development | 2 days
Dev03 | Package and plan page | Development | 2 days
Dev04 | Body Type & Health / Diet Guide page | Development | 2 days
Dev05 | Blogs page creation | Development | 2 days
Dev06 | Our Partners page creation | Development | 2 days
Dev07 | Diet Surveypage creation | Development | 2 days
Dev08 | FAQ page Creation | Development | 2 days
Dev09 | Implementing changes from sprint 2 testing and feedback from client | Development | 1 day
Dev10 | Implementing logo on website | Development | 1 day
Dev11 | Implementing customer feedback until sprint 2 on sites | Development | 1 day
Dev12 | Admin Portal creation | Development | 6 days
Dev13 | Implementing changes from sprint 3 testing | Development | 1 day
Dev14 | Customer feedback implementation | Development | 1 day
Dev15 | Website hosting and database setup, live website | Development | 1 day
Dev16 | Implementing changes and fixing bugs from full testing | Development | 1 day
Dev17 | Making changes on customer feedback | Development | 1 day
Dev18 | Website Live Monitoring | Development | 1 day
30 days
Test01 | Testing for products created on first 2 sprint | Testing | 3 days
Test02 | testing review for sprint 2 submission | Testing | 1 day
Test03 | Testing for products created on first 3 sprint | Testing | 2 days
Test04 | testing review for sprint 3 submission | Testing | 1 day
Test05 | Full website testing | Testing | 2 days
Test06 | Testing review for full testing | Testing | 1 day
10 days

## Timeline
Week | Date | Day | PM Task | Designer Task | Developer Task | Tester Task
1 | 3 | Mon | Discuss with client about look and feel expectation and theme presentation
1 | 4 | Tue |  | Reference and Samples
1 | 5 | Wed | presentation of Sample themes and reference | Website wireframe Design
1 | 6 | Thu
1 | 7 | Fri
| 8 | Sat
| 9 | Sun
2 | 10 | Mon |  | implementation of theme on wireframe and website mockup Draft 1 for all pages.
2 | 12 | Tue
2 | 13 | Wed | Wireframe with theme presentaion and feedback from customer
2 | 14 | Thu |  | Implementing feedback from customer on mockup creating prototype 1
2 | 15 | Fri |  |  | Home/Index page prototype 1 creation
| 16 | Sat
| 17 | Sun
3 | 18 | Mon | sprint meeting | Logo concept sketch | Book free consultation form creation for home page
3 | 19 | Tue | Discuss with client and brainstorm about concept sketch |  | ,, ,,
3 | 20 | Wed |  | Logo 1st Digital draft | Package and plan page
3 | 21 | Thu | Feedback and changes on Logo first Digital draft |  | ,, ,,
3 | 22 | Fri |  | Logo 2nd Digital draft | Body Type & Health / Diet Guide page
| 23 | Sat
| 24 | Sun
4 | 25 | Mon | Feedback and changes on Logo 2nd Digital draft |  | ,, ,,
4 | 26 | Tue |  | Logo final draft | Blogs page creation
4 | 27 | Wed |  |  | ,, ,,
4 | 28 | Thu |  |  | Our Partners page creation
4 | 29 | Fri |  | Applying Final changes and handing over logo to development team | ,, ,,
| 30 | Sat
| 31 | Sun
5 | 1 | Mon | Sprint meet for 3rd sprint |  | Diet Surveypage creation | Testing for products created on first 2 sprint
5 | 2 | Tue |  |  | ,, ,, | ,, ,,
5 | 3 | Wed |  |  | FAQ page Creation
5 | 4 | Thu |  |  | ,, ,, | testing review for sprint 2 submission
5 | 5 | Fri |  |  | Implementing changes from sprint 2 testing and feedback from client
| 6 | Sat
| 7 | Sun
6 | 8 | Mon | Customer feedback for product until sprint 2 |  | Implementing logo on website
6 | 9 | Tue |  |  | Implementing customer feedback until sprint 2 on sites
6 | 10 | Wed |  |  | Admin Portal creation
6 | 11 | Thu |  |  | ,, ,,
6 | 12 | Fri |  |  | ,, ,,
| 13 | Sat
| 14 | Sun
7 | 15 | Mon | Sprint meet for 4th sprint |  | ,, ,, | Testing for products created on first 3 sprint
7 | 16 | Tue |  |  | ,, ,, | ,, ,,
7 | 17 | Wed |  |  | ,, ,, | testing review for sprint 3 submission
7 | 18 | Thu |  |  | Implementing changes from sprint 3 testing
7 | 19 | Fri | Feedback and changes on pages created on sprint 2 from client, Sprint meet 2
| 20 | Sat
| 21 | Sun
8 | 22 | Mon |  |  | Customer feedback implementation
8 | 23 | Tue |  |  | Website hosting and database setup, live website
8 | 24 | Wed |  |  |  | Full website testing
8 | 25 | Thu |  |  |  | ,, ,,
8 | 26 | Fri |  |  |  | Testing review for full testing
| 27 | Sat
| 28 | Sun
9 | 29 | Mon | Customer testing the Website prototype for features and getting feedback |  | Implementing changes and fixing bugs from full testing
9 | 30 | Tue |  |  | Making changes on customer feedback and monitoring live site